## Sheet1
[9 empty] | COUNTDOWN | EVENT WEEK | RETURN |  |  | REPEAT
2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02
BOUNCEBACK Thank you for signing up Call To Action (CTA): Your kit is on its way and get organising (Before resources are live: keep an eye out for your kit which we'll send to you!)
|  | KIT 1 Get planning CTA: Advertise your day / Link to resources |  |  | KIT2 Cause email CTA: Read about the difference your big tea will make |  | KIT 3 Last min tips for organising your day CTA: helpful tips and tools |  | 29th June COUNTDOWN One week to go! CTA: host your big tea on 5th July | 5th July ON THE DAY It's the big day! CTA: Take part, share on social (and pay in) | CHASER 1 Thank you and pay in CTA: Pay in / see how everyone else got on (UGC) | CHASER 2 Pay in CTA: Pay in / the difference you're making |  | FINAL THANK YOU Fundraising total CTA: Complete survey / pay in any more donations
These communications form the stewardship journey which all sign ups to the NHS CT Big Tea will receive. They will be sent by the NHS CT Big Tea team or content will be provided to member charities to send to their sign ups
To ensure flexability between members, emails are shown above in week blocks and can be sent on any date starting the w/c date to all sign ups to date, unless a date is specified. Where a date is specified the email should be sent on the specified date as it is more time dependent.
Core | Nice to have
Bounceback | KIT 1/2/3
On the day | Countdown
Day after
Chaser 1/2/3
Final thank you